## Sheet3
Service Required | Responsible Person/Team | Remarks | Status
Venue - CTEA | Shoba | CTEA is booked for Nov9 th and 10th. 8th arrangements can be done. | Done
Rest Area - Sandipani | Shoba | 5 rooms in Sandipani will be booked. Shailaja to send formal mail to Shoba. | Done
Permissions to stay in the night | Raghavendra | Shailaja will the participants lists including Microsoft member details. | In progress
Security 24 hours | Nalini
Ambulance, transport to hospital in case of emergency | Nalini
Nurse Assistance | Nalini
Video Conferencing , Projector,Mic,speaker ,Telephone Check | Shoba/Ravikumar/Deepak
i)Professional Photography(9th 1.30 to 2 hrs,10th 2 pm 2 hrs) ii)Informal photography | Nalini/Ashwin | Ravikumar /Prashanth will decide
Housekeeping Staffs | Shoba | 1 supervisor + 1 staff
Tea / Coffee | Shoba / Iftekar /Nalini | Ravikumar will give the list. | 95+25, 125
Snacks | Shoba | Ravikumar will give the list.
Food | Shoba | Ravikumar will give the list.
Drinking water facilities | Shoba
Round table for participants with team name | Shoba | Naveen , Divya
Power / Power points | Shoba, Ravikumar
Internet - Public IP with LAN,WiFi & Routers | Ravikumar/Prashnth YP | Collect Wifi Dongles internally available in L&T leaders
Motivation Events | Angela/Sneha
Volunteers identification(TA, Anchor, senior members,IT,HR, admin etc) | Prashanth,Naveen | Nalini (admin) ,Angela(HR),Ashwin(HR),Deepak(IT),Amith Jain(CTEA IT),,DMs
For Monday meeting if we have to book Module II for two Hrs (half a day) it costs Rs. 4000..(Availabilty Rahul is checking) | Shailaja |  | Done
Room booking For one room in Sandipani for 1 night it is rs 2000. For 5 rooms 1 night it becomes Rs.10000 | Shailaja |  | Done
Conf Room availability for Judges | Shailaja/Shoba
Microsoft delegate list (Bangalore, Mysore) | Shailaja/Prashanth YP | YP to write a mail to Microsoft | Done
Update to Microsoft on azure themes | Salman/Prashant YP
Legal document approval | Shailaja
T-Shirt ownership | Ranjini
Laptop , Devices registartion , Gate pass & ownership | Saikumar,Ajay Kumar
Laptop , Device Registration Desk on the day of event | Vinutha D,Abhishek
Markers,discussion board | 30 mrkers, 50 sheets/Lokesh | Ravikumar
Microsoft promotions, others | Prashanth,Naveen
Give the list of participants & volunteers and Microsoft delegates | Shailaja | Gate pass | In Progress
MC, stage management | Snehal & Dhaerya/Ranjini
Volunteers identification(TA, Anchor, senior members,IT,HR, admin etc)
Cake cutting - 5kg | Ravikumar/Nalini
Badge, whistle | Ravikumar/Nalini